## Slide 1: Occupational Burnout
Peak Health Technologies and ISB AMPBA
13th May 2022

## Slide 2: Data set
Underlying data will consist of facet scores with supporting text.
Peak Health data not yet available. Start with synthetic data set created from employee reviews. Replace synthetic data with Peak Health facet data, piece-meal, as it becomes available.
Create analytics and models on this synthetic data. There’s a rough mapping between our “facets” and the “categories” in the data set.
Data set consists of about 100,000 reviews from multiple companies (.csv files). Feel free to add on to this data set.
Each record has:
  Company
  Overall Score
  Job Function
  Location
  Date
  Review text
  Likes (text)
  Dislikes (text)
  Ratings by category (each sub-score is a separate field): Work/life balance, Skill Development, Salary & Benefits, Job Security, Company Culture, Career Growth, Work Satisfaction

## Slide 3: Project phases and deliverables
Phase 1: Reading, Data Exploration, Visualization
  Background reading on Burnout, including: HBR guide to beating burnout
  Deliverable: State of the Workforce dashboard
Phase 2: Facet text Summarization
  eHR
    Deliverable: Digital Watercooler (harness pros, likes, advice, similarities)
    Deliverable: Digital Suggestion Box (harness cons, dislikes, complaints)
Phase 3 : Slice and Dice
  Combine multiple reviews from employees in the same job function, from the same location, into a representative single employee
  Deliverable: StrengthsFinder (compared to other similar employees)
  Deliverable: State of the Workforce comparator (across job functions, locations, etc)
Phase 4: Model
  Deliverable: Prediction model of sub-category scores based on job function, location, review text, features extracted in parts 1,2,3.
Phase 5: Publish
  Jointly publish a research paper or a business article.

## Slide 4: Project Summary
Data:
  Synthetic data set of 100,000 records
  Piece-meal replacement by Peak Health data
Deliverables:
  State of the Workforce
  eHR: Digital Watercooler
  eHR: Digital Suggestion Box
  Strengths Finder
  Prediction model
  Publication
Discussion:
  Weekly zoom call between ISB team and Peak Health (TBD)
Milestones (from AMPBA Charter doc):
  Project Charter Finalization: 20th May 2022
  Weekly Reports: Every Sunday
  Final Presentation to Sponsor: By 10th August 2022
  Final Report Submission: 15th August 2022
  Project Handover to the Sponsor: By 19th August 2022